## Structure
| TASK |  | Deadline | 2022 | [11 empty] | 2023 | [47 empty] | 2024 | [47 empty] | 2025
|  | Beginning |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June
|  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Inheritance of BIRDS-5 | bar: December 1 to December 4
Modifications according to mission requirements | bar: December 3 to January 4
Parts selection and procurement | bar: January 3 to February 4
Configuration Design | bar: February 4 to April 2
Structural analysis (STM) | bar: April 3 to June 3
Design review | bar: June 2 to June 4
Parts selection | bar: July 1 to August 1
| Revision and Integration |  | ` | bar: August 2 to October 4
Structural analysis (EM) | bar: September 1 to October 4
Vibration and shock test (EM) | bar: September 1 to October 4
Design review | bar: November 1 to December 3
CDR documentation | bar: November 1 to December 3
| Flight model integration and testing |  | ` | bar: December 4 to February 3
`
1 | Preliminary announcement |  | 2022-12-25 | bar: December 1 to December 3
2 | 1st Phase | bar: December 4 to February 4
| Call for Participation | 2022-12-26 | bar: December 4 to February 4
Application Deadline | bar: February 4
Evaluation period | bar: March 1 to March 2
Annoucement of selected teams | bar: March 2
3 | 2nd Phase | bar: March 2 to May 4
| Development period |  | ` | bar: March 2 to May 1
Application deadline | bar: May 1
Evaluation period | bar: May 1 to May 3
Annoucement of selected teams of 10 (11) | bar: May 4
4 | 3rd Phase | bar: May 4 to December 4
| Development period |  | ` | bar: May 4 to August 4
| Submittion of EM Board |  | ` | bar: August 4
Evaluation period | bar: September 1 to October 4
Announcement of selected teams 5 (6) final participants
Flight model development | bar: October 4 to December 4
Flight model Arrival | bar: December 4
Note on AJ9: Jorge Casir: Announcement of 10 participants
Note on AV12: Jorge Casir: EM DELIVERY
Note on BD14: Jorge Casir: Announcement of 5 teams
Note on BL17: Jorge Casir: FM Delivery

## Main Schedule
| TASK |  | Deadline | 2022 | [11 empty] | 2023 | [47 empty] | 2024 | [47 empty] | 2025
|  | Beginning |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June
|  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
| Interface Definition (Satellite and Bus) |  | 2022-11-30 | bar: November 4
| MDR / Call for participation APRS |  | 2022-12-28 | bar: December 4
| Selection of APRS payload |  | 2023-03-31
| Preliminary Design Review |  | 2023-05-30 | bar: May 4
| Arrival of APRS mission payload test models |  | 2023-08-30 | bar: August 4
| Critical Design Review |  | 2023-10-30 | bar: October 4
| Arrival of APRS mission payload flight models |  | 2023-12-30 | bar: December 4
| Flight readiness review/ satellite flight model finished |  | 2024-03-30 | bar: March 4
| Hand-over satellite (assuming ISS release) |  | 2024-04-30 | bar: April 4
| Posting technical information in public domain |  | 2024-08-30 | bar: August 4
| Satellite release from ISS and start of Operations |  | 2025-01-30 | bar: September 4
| Publication of results |  | 2023-06-30 | bar: October 4
1 | Preliminary announcement |  | 2022-12-25 | bar: December 1 to December 3
2 | 1st Phase | bar: December 4 to February 4
| Call for Participation | 2022-12-26 | bar: December 4 to February 4
Application Deadline | bar: February 4
Evaluation period | bar: March 1 to March 2
Annoucement of selected teams | bar: March 2
3 | 2nd Phase | bar: March 2 to May 4
| Development period |  | ` | bar: March 2 to May 1
Application deadline | bar: May 1
Evaluation period | bar: May 1 to May 3
Annoucement of selected teams of 10 (11) | bar: May 4
4 | 3rd Phase | bar: May 4 to December 4
| Development period |  | ` | bar: May 4 to August 4
| Submittion of EM Board |  | ` | bar: August 4
Evaluation period | bar: September 1 to October 4
Announcement of selected teams 5 (6) final participants | bar: October 4
Flight model development | bar: October 4 to December 4
Flight model Arrival | bar: December 4
APRS Reference Payload
Testing legacy hardware | bar: December 3 to February 3
Procurement Components | bar: February 1 to March 2
Programming MCU | bar: March 1 to May 1
Testing EM Board | bar: April 4 to August 1
Hardware Integration & Testing | bar: July 3 to October 1
FM board development | bar: October 1 to December 2